## Sheet1
Defect ID | Sprint | Module | Defect Description | Severity | Priority | Status | Reported By | Assigned To | Date Reported | Date Closed | Remarks
DF-01 | Sprint 1 | Data Preprocessing | HTML tags not removed completely in some emails | Medium | P2 | Closed | QA Engineer | Data Engineer | 2025-12-02 | 2025-12-03 | Regex updated
DF-02 | Sprint 2 | Spam Classification | Promotional email misclassified as non-spam | High | P1 | Closed | QA Engineer | ML Engineer | 2025-12-15 | 2025-12-16 | Model retrained
DF-03 | Sprint 2 | Category Classification | Complaint emails classified as general query | Medium | P2 | Closed | QA Engineer | ML Engineer | 2025-12-18 | 2025-12-19 | Feature tuning done
DF-04 | Sprint 3 | Urgency Detection | Keyword “ASAP” not detected in lowercase | High | P1 | Closed | QA Engineer | ML Engineer | 2025-12-27 | 2025-12-27 | Case normalization added
DF-05 | Sprint 3 | Priority Assignment | Medium urgency mapped incorrectly to High priority | Medium | P2 | Closed | QA Engineer | AI Engineer | 2026-01-02 | 2026-01-03 | Logic corrected
DF-06 | Sprint 4 | Streamlit UI | Empty email input causes warning not shown | Low | P3 | Closed | QA Engineer | Frontend Dev | 2026-01-18 | 2026-01-18 | Input validation added